## Sheet1
No | CMWS EMWS | Requestor | Department (Requestor) | Category | Marconi SF(Non-PDL) | Marconi SF PDL | Marconi Base | Marconi PDL Base Specific | Marconi Hi | Marconi PDL Hi Specific | Requirement | Additional Comments/Information | Threshold (Accept) | Goal (Design Target) | Priority | Lead Function | Lead | Co Deliver Team Member | Accept - Goal | Committed to Deliver by | Status | Remarks | Requestor | Department_Requestor | Applicable_SKUs | Cleaned_Requirement_Text | Ambiguity_Flag | Reason_for_Ambiguity | Comment | Verification_Status
1 |  | Celine Taccori | Design | Customer Experience | Y | Y | Y | Y | Y | Y | OOBE - reduce number of steps : 123.hp.com : | Is there a reason to have 3 names for the same reference ? HP OJP 9010 All-in-one Printer series HP OJP 9010e All-in-One Printer series HP OJP 9010 All-in-One Printer Have too many names isn't efficient and can induce user errors | two names / reference are proposed currently 4 references for Office Jet Pro 9010 | Only one name / reference is proposed to customer | MUST | Solution | Chris |  | Drop |  | Grey | Quality team is following-up with Tais Bellini. 20210702 (Chris/Jess) Not possible to change in 123.hp.com as it reference to Product Master List where is common shared with PC group. It is only currently possible to do at support.hp.com. Proposed to Drop. | Celine Taccori | Design | ['Marconi SF(Non-PDL)', 'Marconi SF PDL', 'Marconi Base', 'Marconi PDL Base Specific', 'Marconi Hi', 'Marconi PDL Hi Specific'] | Reduce the number of product references (names) for HP OfficeJet Pro 9010 series on 123.hp.com to a maximum of one, to avoid user confusion and errors. | NO
2 |  | Chong, Shin | HDRV | Reliability | Y | Y | Y | Y | Y | Y | Printer able to run all new/current EM / market segment media | Printer to meet intervention spec for the different media and climatic conditions for Manhattan platform. | Minimum PQ acceptable by region | Pass intervention rate and NO PQ issue | MUST | ME Platform | Sau Pin |  | Accept - Threshold |  | Green | 20220920(Sau Pin): LP2 Life test are meeting Intervention rate(Qual) 20220316 (Sau Pin): I assume baseline is same as Manhattan. Status as "Yellow" as need to review interventon performance. Accept threshold. EM media as Eval media. | Chong, Shin | HDRV | ['Marconi SF(Non-PDL)', 'Marconi SF PDL', 'Marconi Base', 'Marconi PDL Base Specific', 'Marconi Hi', 'Marconi PDL Hi Specific'] | Printer must reliably print on all new and current EM (Evaluation Media) and market segment media, meeting regional intervention specifications and climatic conditions for the Manhattan platform. | NO
3 |  | Chong, Shin | HDRV | Reliability | Y | Y | Y | Y | Y | Y | Product can be placed and work on uneven surface ( sofa , table cloth , carpet …) | As the complain on Vasari , input tray sensor flag broken when printer is placed on uneven surfact , this issue should be fixed in new product | Meet customer requirement | Meet customer requirement | MUST | ME Platform | Sau Pin |  | Accept - Threshold |  | Green | 20220315(Sau Pin): Marconi Base LP1 test with no issue reported. Marconi Hi and PDL SKUs testing on-going HDRV response: Have conducted sanity check with Manhattan Base & Hi, Malbec Hi and Agave. Only Malbec Hi had issue with input tray flag broken. Need TME input on field data for 3M. Aiqiang: Manhattan field data shows tray "fang" broken. ME will look at solutions to solve fang broken issue such as to strengthen the fang. | Chong, Shin | HDRV | ['Marconi SF(Non-PDL)', 'Marconi SF PDL', 'Marconi Base', 'Marconi PDL Base Specific', 'Marconi Hi', 'Marconi PDL Hi Specific'] | Printer must operate without functional or hardware issues when placed and used on uneven surfaces such as sofas, table cloths, or carpets. | NO
4 |  | Chong, Shin | HDRV | Reliability | Y | Y | Y | Y | Y | Y | Tilt left and right each while printing | To assess whether there is any functional failure if customer tilt the printer during printing.(Sayan tilt left and right each at 20 degree while printing ) | Meet customer requirement | Meet customer requirement | MUST | ME Platform | Sau Pin |  | Drop |  | Grey | tilt 20 degree is for CISS product as acknoledged by Michelle. Shin to check if want to evaluate on Manhattan Plus with XXL ink cartridges. Close for Marconi. | Chong, Shin | HDRV | ['Marconi SF(Non-PDL)', 'Marconi SF PDL', 'Marconi Base', 'Marconi PDL Base Specific', 'Marconi Hi', 'Marconi PDL Hi Specific'] | Printer must function without failure if tilted left or right up to 20 degrees while printing. | NO
5 |  | Chong, Shin | HDRV | Reliability | Y | Y | Y | Y | Y | Y | Put printer on trolley and print | To check if there is PQ issue when printer print on trolley. | Meet customer requirement | Meet customer requirement | MUST | ME Platform | Sau Pin |  | Accept - Threshold |  | Green | (Sau Pin): Marconi Base LP1 test with no issue reported. Marconi Hi and PDL SKUs testing on-going interesting to find out the test result. HDRV response: Have conducted sanity check with Manhattan Base & Hi, Malbec Hi and Agave. No issue found. Agree to put it as evaluation. To be consistent with stardard UBT requirement.20220315 | Chong, Shin | HDRV | ['Marconi SF(Non-PDL)', 'Marconi SF PDL', 'Marconi Base', 'Marconi PDL Base Specific', 'Marconi Hi', 'Marconi PDL Hi Specific'] | Printer must print without print quality issues when placed on a moving trolley. | NO